## Slide 1
Week 1 Report
Dental by Design | Prodent Group
Christopher Hoole
Google Ads Specialist | April 2026
christopherhoole.com
Data: Monday 13 – Friday 17 April 2026
Brand Avg CPC Trend
£3.18 → £1.61
−49% week-on-week · lowest of 8 tracked weeks · impression share 92%+
~675
New Keywords Added
25
DII Ad Groups (was 4)
75
New RSAs Written

## Slide 2
Executive Summary
Week 1 · 13-17 Apr
£8,462
Week 1 Spend
87
Dengro Offline Leads
101
Primary Conversions
£97
Cost per Lead
Key Wins This Week
Brand CPC at 8-week low: £2.16 vs March avg £3.29 (−35%). £1.50 Max CPC cap is biting without suppressing volume.
PMax CPA improved week-on-week: £73 vs £85.86 prior week, despite persistent asset-group policy restrictions.
DII entered learning phase after full rebuild: 25 new ad groups, ~675 keywords, 75 RSAs. Clean read expected Week 2-3.
5,000+ structured negatives replaced 2,192 unstructured broad-match entries across 11 shared lists.
Giulio replied Fri 17 Apr with answers — compliance actions captured and scheduled for Week 2.
Week 1 was structural.
Three live campaigns moved off Max Conversion Value bidding onto controllable targets.
Early signal is positive — but DII needs a further week of stabilisation and Monday's end-to-end tracking audit is the gate to any CPA-based decisions from here.
Christopher Hoole | christopherhoole.com | Confidential
2

## Slide 3
Work Delivered
Tue 14 → Fri 17 April · 4 working days post-signing · 28 hours
Foundation Week
Day-by-Day Activity
Day | Focus | Output | Impact
Tue 14 Apr | Negatives Overhaul | 2,192 → ~4,000+ across 11 lists | ~£63k waste blocked
Wed 15 Apr | Account-Wide Reset | Brand · PMax tCPA £60 · DII tCPA £75 | Controllable bid targets
Thu 16 Apr | DII Rebuild (Part 1) | 20 AGs · 537 keywords · 60 RSAs | Patient-intent structure
Fri 17 Apr | Audit + Completion | 173 DBD-blockers removed · AG21-25 built | Campaign 25/25 complete
Running Totals
Positive keywords added: 675 across 25 ad groups
New RSAs written: 75 (1,050 headlines, 280 descriptions)
Negatives: 5,000 structured across 11 shared lists
Geo targets: 270 London postcodes rolled out to all 3 active campaigns
Key Findings
All 3 live campaigns moved from Max Conversion Value to Target CPA / Target Impression Share.
Auto-apply recommendations disabled = no more silent keyword removals.
Zero NHS/free-seeker junk in PMax search terms post-switch - negatives are working.
Asset groups in PMax flagged 'limited by policy' - full rebuild scheduled Wed 22 Apr.
Christopher Hoole | christopherhoole.com | Confidential
3

## Slide 4
Brand Campaign
CPC at 8-week low · £1.50 Max CPC cap is working
Performance
Week 1 Performance
Metric | Week 1 | Prior Week | Change
Week spend | £280 | £298 | −6%
Primary conv | 12.0 | 12.0 | Flat
Cost / conv | £23.39 | £24.89 | −6%
Key Finding
Brand CPC is at its lowest of 8 tracked weeks: £2.16 vs March avg £3.29 (−35%).
The £1.50 Max CPC cap (set Wed 15 Apr) is biting without suppressing volume.
Impression share held at 92%+ and conversion volume tracked with spend.
This is the strongest signal of Week 1.
Bid Strategy Applied
From: Max Conversion Value (tROAS 10%) - inflating brand CPCs To: Target Impression Share 90% · Max CPC £1.50
Goal: eliminate runaway bidding on brand traffic, lock in the brand position at controlled cost
Result: CPC dropped from £3.18 (prior 30d) to £1.61 (first 36 hours) to £2.16 (week avg)
Next Week
Hold the £1.50 cap through Week 2. Let the bid strategy complete its 14-day learning phase.
Evaluate lowering toward £1.20 once CPC has stabilised at or below £1.50.
Brand is mature territory, small incremental CPC reductions compound into meaningful monthly savings.
Christopher Hoole | christopherhoole.com | Confidential
4

## Slide 5
Performance Max
CPA improved week-on-week despite policy restrictions
Performance
Week 1 Daily CPA
Day | Spend | Primary Conv | CPA
Mon 13 Apr | £2,017 | 17 | £119
Tue 14 Apr | £558 | 10 | £56
Wed 15 Apr | £402 | 16 | £25
Thu 16 Apr | £1,792 | 23.5 | £76
Fri 17 Apr | £1,188 | 15 | £79
Week total | £5,960 | 81.5 | £73.13
What Changed & What's Next
Bid Strategy Switch
From: Max Conversion Value (tROAS 80%)
To: Target CPA £60
Drove campaign to optimise for LEAD VOLUME at controllable cost, not arbitrary £300 booking values
Wed 15 Apr: first full day under new strategy delivered £25 CPA, best single day in the account
Flagged for Week 2
Google still reports 'most asset groups limited by policy'
This restricts PMax reach, it's not running at full potential
Full asset rebuild scheduled Wed 22 April
Stripping unverified claims: '99.12% success', 'Save 60%', 'Top 10 Europe'
Replacing with policy-safe copy aligned to Giulio's verified claims
Recommendation
Hold the new bid strategy untouched, let Google complete its 7-day learning cycle.
PMax asset rebuild addresses the policy flag next week.
Expected upside: lifting policy limits typically unlocks 2-3× reach at the same CPA.
Christopher Hoole | christopherhoole.com | Confidential
5
Week 1 Story
Bid strategy switched Wed 15 April, at the midpoint of the week. Each day tells a different part of the story:
Mon 13 & Tue 14
Operating under the old tROAS strategy with characteristic swings, £119 and £56 CPA.
Wed 15
First partial day under new Target CPA £60, delivered £25 CPA, the best single day in the account.
Thu 16 & Fri 17
Fully post-switch, settling toward the £60 target at £76 and £79 CPA.
Week-total CPA: £73.13 vs prior week £85.86, a 15% improvement despite policy restrictions.

## Slide 6
Dental Implants Intent
Fully rebuilt Thu–Fri · 4 ad groups → 25 · entered learning phase
Rebuild
Metric | Before (legacy) | After (new) | Change | Impact | Status
Ad groups | 4 (paused) | 25 live | +525% | Patient-intent grouped | Complete
Keywords | 27 | ~675 | +2,400% | Phrase + exact | Complete
RSAs | 6 (Poor-rated) | 75 | +1,150% | Keyword-aligned | Complete
Headlines | ~90 | 1,050 | +1,067% | Unique, keyword-rich | Complete
Descriptions | ~24 | 280 | +1,067% | 75-86 chars (QS safe) | Complete
Legacy AG CPA | £99+ avg | Paused | Eliminated | Waste removed | Done
Bid strategy | Max Conv Value (tROAS) | Target CPA £75 | Controllable | Lead-focused | Learning
Geo | 25-mile radius | 270 London postcodes | M25 targeting | 4-tier structure | Rolled out
Schedule | Always on | 42-cell structure | Hourly analysis | Reporting ready | Live
Learning phase | n/a | Day 1 of 14 | In progress | 7-14 days to stabilise | Monitor
Campaign status | Scaling with waste | Learning - clean base | Foundation set | Week 2-3 read | On track
Key Finding
The DII campaign was fully restructured mid-week (Tue → Fri).
Week 1 CPA blends 1 day of the old structure with 4 days of Google's learning phase, expected noise, not signal.
Google requires 14-21 days to rebalance bids against the new structure.
First clean performance read: Week 2-3.
Recommendation
Hold the new structure untouched through Wed 22 April.
Ad Strength audit on AG22-25 resumes Tuesday once Google clears the new ads from Pending review.
Second pass on AG1-21 to push remaining RSAs toward Excellent.
Christopher Hoole | christopherhoole.com | Confidential
6

## Slide 7
The Numbers That Matter
Business outcomes — what the account delivered this week
Business Outcomes
Week 1 at a Glance
Metric | Week 1 | Prior Week | Change | Status
Total Spend | £8,462 | £10,291 | −18% | Trimmed
Dengro Offline Leads | 87 | — | — | Tracking
Primary Conversions | 101 | 134 | −25% | Learning
Key Signal
87 Dengro Offline Leads generated this week across 3 active campaigns.
Performance Max delivered 90% of qualified leads (78.5 of 87).
Dengro Offline Booking fired 0 times, tracking gap flagged for Monday's audit.
No CPA-based decisions will be drawn before the audit closes.
Week 1 Conversion Breakdown
Campaign | Spend | Primary | Dengro Leads | Cost/Lead
Performance Max | £5,960 | 81.5 | 78.5 | £75.92
Dental Implants Intent | £2,222 | 7.5 | 6.5 | £341.83
Brand | £280 | 12.0 | 2.0 | £140.24
TOTAL | £8,462 | 101.0 | 87.0 | £97.27
[molar replacement cost] | 3 | £159 | £40 | Below average
Dengro Offline Booking fired 0 times in Week 1. Monday's tracking audit will confirm whether this is a reporting gap or a genuine zero-booking week.
Christopher Hoole | christopherhoole.com | Confidential
7

## Slide 8
8-Week Context
Weekly performance trend · 23 Feb – 17 April 2026 · spend, conversions, CPA
8-Week Trend
Weekly Performance
Week | Spend | Primary Conv | CPA
23 Feb | £17,568 | 237.5 | £74
2 Mar | £14,856 | 189.6 | £78
9 Mar | £8,393 | 120.3 | £70
16 Mar | £13,318 | 137.7 | £97
23 Mar | £11,558 | 239.2 | £48
30 Mar | £9,997 | 148.4 | £67
6 Apr | £10,291 | 134.1 | £77
13 Apr | £8,462 | 101 | £84
30 Mar | £9,997 | 148.4 | £67
6 Apr | £10,291 | 134.1 | £77
13 Apr | £8,462 | 101 | £84
Key Observation
Weekly spend fluctuated dramatically: £17.5k peak (23 Feb) → £8.4k (Week 1). A 52% range in 8 weeks.
CPA swung from £48 (best week) to £97 (worst week) — highly volatile before our engagement.
Additional weeks: 30 Mar £9,997/£67 CPA · 6 Apr £10,291/£77 CPA · 13 Apr £8,462/£84 CPA
Week 1 (13 Apr) reflects 5 days of structural disruption: new bid strategies, rebuilt campaigns, changing keyword base.
Week 1 in Context
Weekly spend volatility has been the account's core instability — this rebuild brings it under control.
Target: stabilise weekly spend within a consistent range aligned to your target monthly budget (see Questions slide).
Efficiency (cost per lead) is the metric to watch from Week 3 onwards, once the rebuild stabilises.
First clean performance read: Week 2-3 after Google's learning phase completes.
Monday's tracking audit confirms conversion reliability — the gate to CPA analysis.
Week 2 performance comparison vs Week 1 will be the first post-rebuild read.
Please confirm target monthly budget so I can lock weekly pacing (see Slide 10).
Christopher Hoole | christopherhoole.com | Confidential
8

## Slide 9
Client Clarifications & Actions
Giulio replied Fri 17 April 16:47 · actions captured
Client Reply
Confirmed by Giulio
Consultation: Free + £25 booking deposit
Lead → Booking rate: 13%
Booking → Treatment rate: 35%
Patient base: 10,000 patients, 20,000+ implants placed
25+ years team-wide expertise in dental field
Compliance Actions Required
Remove '99.12% success rate' from all ads — confirmed estimate
Remove 'Save 60%' — no source benchmark
Reword 'Top 10 Europe' → factual descriptor (self-claim, not award)
Reword 'Best Implant Clinic 2024' → '2024 Finalist'
Update ad copy: 'Free Consultation (£25 booking deposit)'
Advertising Scope
DBD only advertises dental implants (single + double arches) — confirmed by Giulio.
Cosmetic and general dentistry services deferred for now.
All campaigns aligned to this focus: Brand, PMax, Dental Implants Intent.
Applying all compliance changes Monday 20 Apr: removing unverifiable claims, updating consultation pricing.
Replacing '2,500+ patients' claim with '20,000+ implants placed' across relevant ads.
AG22-25 Ad Strength audit resumes Tuesday (ads currently Pending Google review).
Christopher Hoole | christopherhoole.com | Confidential
9

## Slide 10
Questions for Client
To refine strategy, I need clarification on a few things
Your Input
Budget Questions (Urgent)
Question | Why It Matters | Answer Needed By
What is your target monthly ad spend? | Weekly spend fluctuated £8k-£17k over 8 weeks. Target budget drives bid and budget decisions. | Mon 20 Apr
What is your target weekly ad spend? | Weekly consistency drives campaign pacing. Current daily budgets sum to ~£14k/week but actual is ~£8.5k. | Mon 20 Apr
Is there a hard monthly ceiling? | Prevents overspend and informs daily budget caps across 3 campaigns. | Mon 20 Apr
Priority service: single or double arch? | Higher-margin service should carry higher bid caps and budget share. | 1 week
How to Reply
Reply to this email with answers to any questions — no need to answer all at once.
Or we can cover these on a 20-30 min call whenever convenient.
Urgent questions (budget) need answers by Monday so Week 2 work isn't blocked.
Why These Matter
Every piece of clarification feeds directly into bid strategies, budget allocation, and ad copy.
The more I know about your business, the more precisely I can tune the account.
Example: the 8-week spend volatility (£8k-£17k range) is what happens when budgets aren't locked to a target — pinning your target spend eliminates this.
Christopher Hoole | christopherhoole.com | Confidential
10

## Slide 11
Week 2 Plan
5 Working Days
Monday 20 Apr — Tracking Audit
Verify form_submit fires on all landing pages End-to-end validation across every Search campaign LP
Verify Dengro Offline Lead / Booking / Purchase reliability
Confirm why Bookings fired 0 times in Week 1 — reporting gap or genuine zero?
Audit attribution windows and conversion counting
Ensure Dengro leads aren't being double-counted or missing
Gate for all CPA analysis. No CPA-based decisions until tracking is confirmed reliable
Tue 21 – Thu 23 Apr — Execution
Apply Giulio's claim corrections across all ads (Tue) Remove 99.12%, Save 60%; reword Top 10, Best Clinic
Resume AG22-25 Ad Strength audit once Google clears Pending (Tue)
RSAs to audit once review completes
Second pass on AG1-21 ads not yet at Excellent (Tue) Push remaining RSAs over the line
PMax asset rebuild (Wed) Policy-safe copy, verified claims only, restores full reach
Ad extensions deployed (Thu) Sitelinks, callouts, structured snippets, first time the account has a complete set
Friday 24 Apr — Review + Report
7-day performance comparison vs Week 1 Spend, leads, CPA — first post-rebuild signal
Brand matures, PMax settles, DII still learning Different campaigns on different learning trajectories
Week 2 end-of-week report delivered EoD Friday
Same format as this report — trend, insights, Week 3 plan
Week 2 is about execution: tracking audit unblocks CPA analysis, claim corrections unblock compliance, PMax rebuild unblocks reach.
Christopher Hoole | christopherhoole.com | Confidential
11

## Slide 12
What's Next
Rolling priorities beyond Week 2
1. Cosmetic dentistry campaign build
2. Landing page optimisation
3. Long-tail keyword expansion
4. Conversion rate improvements
5. Monthly review cycle
6. End-of-month report
Coming Next
Week 2 Report
Weekly performance review,
tracking audit findings,
PMax rebuild results,
Week 3 plan. Delivered EoD Friday 24 April.
4
Compliance Actions
5
Working Days
Week 2
Coming Next