## Slide 1
WEEKLY PERFORMANCE REPORT
Week 1
Account Overhaul | Foundation Build
Dental by Design | Prodent Group
13 April – 17 April 2026
£8,462
Total spend
87
Qualified leads
4
Patient enquiries
£97
Cost per lead
Christopher Hoole
Google Ads Specialist | christopherhoole.com

## Slide 2
2 / 11
Christopher Hoole | christopherhoole.com | Confidential
2
Executive Summary
Week 1 headlines — a foundation week
£8,462
Total Spend
87
Dengro Leads
4
Patient Enquiries
£97
Cost / Lead
Week 1 at a Glance
WHAT I DELIVERED
4,700+ negatives structured into 11 shared listsBrand campaign rebuilt on tIS 90% / £1.50 max CPCDental Implants Intent re-engineered — 25 ad groups, 75 RSAsPMax switched to Target CPA £60173 DBD-blocking terms caught + removed63 live RSAs audited toward Excellent
EARLY SIGNAL
Brand CPC £3.29 → £2.16 (-35%)Brand CTR 35.14% vs 26% prior avgBrand Impression Share 100% top of pagePMax best day £25 CPA (Wed 15 Apr)Search terms quality zero NHS/abroad junk this weekDII in Google Learning mode — clean read in Week 2-3
WHAT'S NEXT
Mon 20 Apr Conversion tracking auditTue 21 Apr AG22-25 Ad StrengthWed-Thu PMax asset rebuildFri 24 Apr Cosmetic campaign scoping + Week 2 report
Awaiting your decision on two items: consultation pricing and the "25+ years" claim. See slide 10.

## Slide 3
3 / 11
Christopher Hoole | christopherhoole.com | Confidential
3
Work Delivered
Day-by-day, 14-17 April (client signed Mon 14 Apr)
Four active working days — ~20 hours of deep structural rebuild
DAY | FOCUS | OUTPUT
Tue 14 Apr | Negative keyword overhaul | 4,700+ negatives restructured into 11 organised shared lists — competitors, abroad, wrong locations, non-DBD services, brand-specific research, and cheap/NHS-seeker traffic.
Wed 15 Apr | Brand rebuild + account-wide | Brand: Target Impression Share 90% / £1.50 max CPC, 266 London postcodes, 42-cell ad schedule, 2 new RSAs. Account: auto-apply disabled, PMax → Target CPA £60, DII → Target CPA £75, 8 new RSAs, 356 more negatives.
Thu 16 Apr | Dental Implants Intent rebuild | 20 new ad groups built, 537 keywords added, 60 RSAs written. 4 legacy under-performing ad groups paused (£99+ CPA). Ad structure mapped to patient intent: service, cost, finance, location, quality.
Fri 17 Apr | Final ad groups + full audit | AG21-25 built (5 ad groups, 15 RSAs). 1,786 daily search queries reviewed. 173 DBD-blocking terms caught and removed across all 11 negative lists. Ad Strength audit across 63 live RSAs to push toward Excellent.

## Slide 4
4 / 11
Christopher Hoole | christopherhoole.com | Confidential
4
The Foundation
What's now in place after this week's rebuild
5,000+
Negative Keywords
11 structured lists
546
Positive Keywords
Brand + DII, structured
75
New RSAs
1,050 headlines / 280 descs
25
DII Ad Groups
patient-intent themed
810
Geo Targets
Gtr London, 3 campaigns
FROM LEGACY PATCHWORK → CLEAN, STRUCTURED ACCOUNT
AREA | BEFORE (pre-engagement) | AFTER (Fri 17 Apr)
Campaign count | 47 campaigns (only 4 active, 43 legacy) | 3 active, structured campaigns
Bid strategy (DII + PMax) | Max Conversion Value (tROAS) — arbitrary £300 values | Target CPA £75 (DII) / £60 (PMax) — real cost control
Negative keywords | Unstructured broad-match, 2 legacy lists, DBD-blocking | 11 organised lists, 5,000+ negatives, DBD-safe
DII ad group structure | 4 legacy ad groups averaging £99+ CPA | 25 ad groups mapped to patient intent
Geo targeting | 25-mile radius (Reading → Romford), 1 rogue Pakistan target | 270 Greater London postcodes, 4-tier structure

## Slide 5
5 / 11
Christopher Hoole | christopherhoole.com | Confidential
5
Brand Campaign
Tighter targeting is already showing
-35%
Avg CPC vs March
£3.29 → £2.16
35.14%
Click-Through Rate
vs 26% March avg
100%
Impression Share
top of page, absolute top
Chart: Brand Avg CPC — 8 week trend
| 23 Feb | 2 Mar | 9 Mar | 16 Mar | 23 Mar | 30 Mar | 6 Apr | 13 Apr
Avg CPC (£) | 3.09 | 2.41 | 3.49 | 4 | 3.24 | 2.31 | 2.9 | 2.16

## Slide 6
6 / 11
Christopher Hoole | christopherhoole.com | Confidential
6
Performance Max
Delivering the bulk of qualified leads
78.5
Dengro Leads
3
Patient Enquiries
£73
CPA (primary)
£25
Best-day CPA
£86 prior week → £73 this week. Wednesday 15 April hit £25 CPA (best single-day in the account) after the Target CPA switch.
WHAT CHANGED THIS WEEK
Bid strategy switched Max Conv Value (tROAS 80%) → Target CPA £603 dangerous negatives removed single-word exacts blocking DBD postcodes (stratford, southall, twickenham)Geo + ad schedule aligned 270 postcodes, 42-cell scheduleShared negative lists cleaned zero NHS/cheap/abroad junk in search terms this week
FLAGGED FOR WEEK 2
Asset groups limited by policy Google still flags "most asset groups limited by policy" — PMax is not running at full potential until this is resolved.
Planned fix: Full asset rebuild Wed-Thu Week 2. Strip unverified claims ("99.12% success", "Voted #1 UK", "Save 60%") and replace with premium-positioned, verifiable assets aligned to the £1,695-£15,990 service range.
Expected upside: lifting policy limits typically unlocks 2-3× reach at the same CPA.

## Slide 7
7 / 11
Christopher Hoole | christopherhoole.com | Confidential
7
Dental Implants Intent
In Google Learning mode — by design
25
New Ad Groups
75
RSAs Live
~650
Keywords
63%
Impression Share
WHY WEEK 1 CPA IS NOT THE CLEAN READ
The campaign was fully restructured mid-week (Tue-Thu):• 20 new ad groups built + 4 legacy groups paused• Bid strategy switched to Target CPA £75• Keyword base rebuilt from the ground up (537 new keywords)• On Fri 17 Apr, AG21-25 added — bringing the structure to 25 ad groups
Google requires 14-21 days to rebalance bids against a restructured campaign. Week 1 CPA blends 1 day of the old structure with 4 days of Google's learning phase. Week 2-3 is when we get the first clean performance read.
Early positive: Wednesday 15 April delivered 3 primary conversions at £122 CPA — the first sign the new structure is converting. The DII impression share climbed to 76% on Thursday and 58% on Friday, confirming the new ad groups are winning their intended auctions.

## Slide 8
8 / 11
Christopher Hoole | christopherhoole.com | Confidential
8
The Numbers That Matter
Real business outcomes — Dengro CRM data
87
Qualified Dengro Leads
at £97 per qualified lead across all campaigns
4
Patient Enquiries (Bookings + Purchases)
£2,115 per enquiry — strong vs implant £1,695-£15,990 LTV
CAMPAIGN | DENGRO LEADS | PATIENT ENQUIRIES | SPEND | £ / LEAD | £ / ENQUIRY
Brand | 2 | 0 | £280 | £140 | —
Dental Implants Intent | 6.5 | 1 | £2,222 | £342 | £2,222
Performance Max | 78.5 | 3 | £5,960 | £76 | £1,987
WEEK 1 TOTAL | 87 | 4 | £8,462 | £97 | £2,115

## Slide 9
9 / 11
Christopher Hoole | christopherhoole.com | Confidential
9
Eight-Week Context
Where the account sits vs prior 7 weeks
Chart: Weekly Spend (£)
| 23 Feb | 2 Mar | 9 Mar | 16 Mar | 23 Mar | 30 Mar | 6 Apr | 13 Apr
Weekly Spend (£) | 17101 | 14475 | 8115 | 13173 | 11558 | 9997 | 10291 | 8462
Chart: Primary Conversions
| 23 Feb | 2 Mar | 9 Mar | 16 Mar | 23 Mar | 30 Mar | 6 Apr | 13 Apr
Primary Conversions | 229.5 | 184.6 | 115.7 | 133.7 | 239.2 | 148.4 | 134.1 | 101
READING THE CONTEXT
Weekly spend was trimmed from ~£17K to £8.5K — intentional. The previous setup was optimising toward arbitrary £300 booking values via Max Conv Value bidding. Switching to Target CPA + paused legacy campaigns tightened spend to converting traffic only.
Primary conversion volume dipped to 101 in Week 1 — expected. The account is in Google Learning mode while the new bid strategy and ad group structure rebalance. All-conversions (including Dengro leads) reached 231 — our real business-signal metric.
Week 2-3 will show the true impact once Learning completes.

## Slide 10
10 / 11
Christopher Hoole | christopherhoole.com | Confidential
10
What's Next
Two decisions needed + Week 2 plan
2 DECISIONS NEED YOUR CALL
1
Consultation pricing
Ads currently say "Free Consultation". Website says £95. Need to align — free, £95, or tiered by service — so ads match reality and clear Google's misleading-pricing policy.
2
"25+ Years" experience claim
Ads reference "25+ years" — clinic founded 2010 (16 years). Clarify whether this refers to the principal's personal experience, combined team years, or something else. Ads will be updated to a verifiable claim.
Awaiting your reply to refine ads in Week 2
WEEK 2 PLAN (20 – 24 APRIL)
Mon 20 Apr
End-to-end conversion tracking audit (priority — before any CPA decisions)
Tue 21 Apr
Resume Ad Strength audit on AG22-25 once Google approves them
Wed 22 Apr
Performance Max asset rebuild — lift the policy limit
Thu 23 Apr
Sitelink + callout + structured snippet extensions across all campaigns
Fri 24 Apr
Cosmetic Dentistry campaign scoping + Week 2 report

## Slide 11
11 / 11
Christopher Hoole | christopherhoole.com | Confidential
11
Questions?
Happy to walk through any part of this report — or jump on a 20-minute call to align on Week 2 priorities.
Christopher Hoole | Google Ads Specialist
christopherhoole.com | chrishoole101@gmail.com