## Slide 1
MONTHLY
OPTIMISATION PLAN
Objection Experts
Prepared by Christopher Hoole
Google Ads Specialist | April 2026
christopherhoole.com
Target KPI
£25 CPA
Cost per lead target
2 hrs/week
Every Monday
3 months
Initial plan horizon

## Slide 2
Optimisation Cadence
2 hours every Monday — consistent, data-driven improvement
Every Monday (recurring tasks)
Search term review — exclude irrelevant terms, identify new keyword opportunities
Performance check — CPA, conversion rate, spend pacing, Quality Score changes
Bid adjustment review — refine schedule, device, and geographic bids based on latest data
Negative keyword maintenance — add new phrase/exact negatives from search term findings
MONTH 1
April 2026 — Foundation
Week 1: Keywords, search terms, new ads
Week 2: Landing page planning + build
Week 3: Landing page live + first data review
Week 4: Performance analysis, CPA adjustment, Month 1 report
MONTH 2
May 2026 — Optimisation
QS monitoring post landing page
Target CPA reduction (£30 → £27)
Ad copy testing cycle 2
Geographic bid refinement
Keyword expansion
MONTH 3
June 2026 — Growth
Target CPA at £25
Full Q2 vs Q1 comparison
Consider PMax campaign retest
Landing page A/B test
Quarterly review with Owen
Christopher Hoole | christopherhoole.com | Confidential
2

## Slide 3
Month 1 — Week 1 (2 April)
Keywords, Search Terms & Ad Copy
Keyword Audit (45 mins)
Review all active keywords against search term performance data
Add high-converting search terms as new keywords (e.g., "planning objection solicitor", "object planning permission", "planning objection advice")
Check match types — ensure phrase match is used for core terms
Verify re-enabled keywords are accruing impressions
Search Term Exclusion (45 mins)
Bulk review all search terms from the past 30 days
Exclude irrelevant terms — add to appropriate negative keyword list by word count
Identify any new waste patterns not covered by existing negatives
Document all exclusions for the monthly report
Ad Copy Review (30 mins)
Assess performance of current 3 RSAs + 1 call-only ad
Build 1-2 new RSA variants for split testing (Trust, Speed, or Value angles)
Review headline and description combinations for relevance
Ensure keyword insertion is working correctly
Christopher Hoole | christopherhoole.com | Confidential
3

## Slide 4
Month 1 — Week 2 (7 April)
Search Terms + Landing Page Build
Search Term Review (30 mins)
Weekly recurring: review new search terms, exclude irrelevant, add promising ones as keywords
Landing Page Planning & Build (90 mins)
Get Owen's current site files — map brand assets (colours, fonts, logos, imagery)
Wireframe new dedicated landing page for planning objection keywords
Shorter, more focused than homepage — headline, form, trust signals, 1 CTA
Build in Claude Code (HTML/CSS/JS), matching objectionexperts.com brand perfectly
Owen to set up Vercel + GitHub accounts — connect repo for continuous deployment
Target: LP draft ready for review by end of session
Landing page goal: Improve "Landing Page Experience" from Below Average to Average/Above Average — the #1 Quality Score lever.
Christopher Hoole | christopherhoole.com | Confidential
4

## Slide 5
Month 1 — Week 3 (14 April)
Landing Page Live + First Performance Review
Search Term Review (30 mins)
Weekly recurring: review, exclude, add keywords
Landing Page Launch (30 mins)
Final review and QA of landing page on Vercel preview
Owen adds DNS records to connect subdomain (e.g., lp.objectionexperts.com)
Push live, verify tracking is firing correctly (form submissions, phone clicks)
Update Google Ads final URLs to point to new landing page
First Performance Review (60 mins)
2 weeks of data since Day 1 changes — first meaningful comparison
Check: CPA trend (is £30 target holding?), conversion rate, click volume
Check: Are re-enabled keywords getting impressions and converting?
Check: Negative keywords working? Any new irrelevant terms slipping through?
Check: Ad schedule and geographic bid adjustments — any obvious outliers?
Document findings for month-end report
Christopher Hoole | christopherhoole.com | Confidential
5

## Slide 6
Month 1 — Week 4 (21 April)
Full Analysis + CPA Adjustment + Month 1 Report
Search Term Review (20 mins)
Weekly recurring: review, exclude, add keywords
Full Month Performance Analysis (60 mins)
3 weeks of data post Day 1 changes — compare to pre-change baseline
CPA trend: is £30 target achievable? Reduce to £27 if data supports it
Quality Score check: has landing page improved LP Experience score?
Ad copy: which RSAs are winning? Pause worst performer if clear loser
Geographic: first month of county-level data — any clear winners/losers?
Device and schedule: refine any bid adjustments with 3 weeks of clean data
Month 1 Report for Owen (40 mins)
Build monthly report: what changed, performance comparison, next month's focus
Include: CPA before vs after, conversion rate, Quality Score changes
Include: specific actions taken and their measured impact
Schedule call with Owen to walk through findings
Christopher Hoole | christopherhoole.com | Confidential
6

## Slide 7
Month 2 — May 2026
Optimisation phase — refine what's working, fix what isn't
Quality Score Monitoring
Track QS changes after landing page launch. Target: move core keywords from QS 2-3 to QS 5-6. This directly reduces CPC.
Target CPA Reduction
If CPA is stable at £30, reduce to £27. Gradual steps — never more than 15-20% at a time.
Ad Copy Testing Cycle 2
Review Month 1 ad test results. Replace worst performing RSA with a new challenger. Test different angles.
Geographic Bid Refinement
Full month of county-level data available. Increase bids on top performers, reduce on underperformers.
Keyword Expansion
Promote best converting search terms to keywords. Review close variants. Consider new ad groups if a theme emerges.
Weekly Search Term Reviews
Continue every Monday — this never stops. The negative keyword lists will grow and protection will improve.
Christopher Hoole | christopherhoole.com | Confidential
7

## Slide 8
Month 3 — June 2026
Growth phase — scaling what works
Target CPA at £25
If QS improvements have taken effect, push target CPA to £25. This should yield 60+ leads per month at the £1,500 budget.
Full Quarter Comparison
Q2 2026 vs Q1 2026 vs Q4 2025 — demonstrate the trajectory. CPA, conversion rate, lead volume, Quality Score, impression share.
PMax Campaign Retest
The old PMax campaign had a £9.73 CPA with 20 conversions. With the account now clean, a PMax retest could unlock additional volume at low CPA.
Landing Page A/B Test
If baseline LP is performing, test a variant (different headline, form placement, or social proof). Small improvements compound.
Quarterly Strategy Review
Call with Owen to review 3 months of progress. Discuss budget, goals, and strategy for Q3. Present the data, agree the next quarter's plan.
Christopher Hoole | christopherhoole.com | Confidential
8

## Slide 9
CPA Reduction Roadmap
Target: £38.63 → £25 within 3 months
£30
Day 1
(Today)
Target CPA set.
Quick wins implemented.
£27
Week 4
(21 Apr)
First reduction.
If CPA stable at £30.
£25
Week 8
(19 May)
Target achieved.
QS improvements active.
£20-25
Month 3
(June)
Sustained performance.
Landing page + QS gains.
What Drives Each Reduction
£38 → £30: Conversion tracking fix + target CPA guardrail + negative keywords (already done)
£30 → £27: Re-enabled high-performing keywords + schedule/geo bid optimisations reducing wasted spend
£27 → £25: Quality Score improvements from dedicated landing page — lower CPCs across all keywords
£25 sustained: Ongoing weekly optimisation, ad copy testing, keyword expansion, geographic refinement
Christopher Hoole | christopherhoole.com | Confidential
9